## FSR Table
FSR Section | Test Name | Success Criteria | Methodology | Ownership | Staus
3.2.1.1 | Zip File Path Identification (RGB) | The code created will identify if there is an existing file path that was generated by the user, and depending on the result, will either let the generation continue, or stop the generation and notify the user a file path exists. Can run for multiple cases for accessing different types of data and attributes. | Using Python and SQL code to identify filepaths and send a printed response to the console. A boolean function will be created to pass a binary 1 or 0 to let the main.js know whether to cancel or continue with the generation. | RONALD | VALIDATED
3.2.1.2 | EPSG Calculation (RGB) | The code created will pass the EPSG from the created project added and be used to properly project the shapefile to the orthomosaic when viewing the data | Similar to how the RGB code has been setup, but with the different types of multispectral data instead and testing for each attribute and for multiple files. | RONALD | VALIDATED
3.2.1.3 | File Path Deletion (RGB) | Once the data has been generated and it has been 2 weeks since the generation, the filepath and the contents in the path will be deleted. Can run for all attributes and for any number of files. | Using Python and SQL code to implement a timer in the background of the website to keep the generated file path for 2 weeks. Using a similar structure to identifying file paths, the code used for deletion will generate after the attribute is generated. | RONALD | VALIDATED
3.2.2.1 | User Friendliness (RGB) | The tested user is able to go through the website relatively easily and with minimal confusion. | I will have friends try out the website to see how they perform | ROSENDO | VALIDATED
3.2.2.2 | UI Restrictions (BOTH) | The UI is able to successfully display files based on restrictions and selected files. | Select different files and constraints to see if the UI successfully updates based on selected files | ROSENDO | VALIDATED
3.2.2.3 | Warnings (RGB) | Based on what type of error occurs the user is notified through popups and warnings. | Run through all possible errors that can occur and make sure each one has a pop up that lets the user know what went wrong. | ROSENDO | VALIDATED
3.2.3.4 | Merged CSV data (RGB) | Within the attribute zip files, there is a single CSV file containing the merged data sets of the individual data sets for a specific attribute. | Examining the generated CSV files individaully and verifying that the data contained in the merged CSV file is correct and doesnt have any overlapping or missing data. This is done through Excel. | CAMPBELL | VALIDATED
3.2.3.5 | Merged SHP data (RGB) | Within the attribute zip files, there is a single SHP file containing the merged data sets of the individual data sets for a specific attribute. | Examining the generated SHP files individaully and verifying that the data contained in the merged SHP file is correct and doesnt have any overlapping or missing data. This is done through QGIS LTR. | CAMPBELL | VALIDATED
3.2.3.6 | Merged CSV data (multispectral) | Within the multispectral zip files, there is a single CSV file containing the merged data sets of the individual data sets for a specific multipectral attribute. | Examining the generated CSV files individaully and verifying that the data contained in the merged CSV file is correct and doesnt have any overlapping or missing data. This is done through Excel. | CAMPBELL | NOT TESTED
3.2.3.7 | Merged SHP data (multispectral) | Within the multispectral zip files, there is a single SHP file containing the merged data sets of the individual data sets for a specific multipectral attribute. | Examining the generated SHP files individaully and verifying that the data contained in the merged SHP file is correct and doesnt have any overlapping or missing data. This is done through QGIS LTR. | CAMPBELL | NOT TESTED

## 404 Gantt Chart
Case | Ownership | Due | 2023-01-27 | 2023-02-10 | 2023-02-24 | 2023-03-10 | 2023-03-24 | 2023-04-07 | 2023-04-14 | Legend
Generating attributes with the selection of multiple files for RGB data. |  | 2023-01-27 | [7 empty] | Ownership | bar: 2023-01-27
Files successfully downloaded from the website in a zip file. |  | 2023-01-27 | [8 empty] | Ronald | bar: 2023-01-27
Implement & test more specific grouping and file zipping based around attributes. |  | 2023-02-10 | [8 empty] | Rosendo | bar: 2023-02-10
Test function that will zip together all of the seperate attribute zip files. |  | 2023-02-10 | [8 empty] | Campbell | bar: 2023-02-10
Implement & test merging together CSV files for RGB data. |  | 2023-02-24 | [8 empty] | All | bar: 2023-02-24
Implement & test merging together SHP files for RGB data. |  | 2023-02-24 | [7 empty] | Progression | bar: 2023-02-24 to 2023-03-10
Implement & test NDVI attribute generation and storage. |  | 2023-03-10 | [8 empty] | Completed | bar: 2023-03-10 to 2023-03-24
Implement & test NDRE attribute generation and storage. |  | 2023-03-24 | [8 empty] | In Progress | bar: 2023-04-07
Implement & test MSAVI attribute generation and storage. |  | 2023-03-24 | [8 empty] | Pending | bar: 2023-04-07
Finish validating subsystem from 403 |  | 2023-01-27 | [8 empty] | Dropped | bar: 2023-01-27
Attribute restriction setups |  | 2023-03-10 | bar: 2023-01-27 to 2023-03-10
Population of dropdown menus with new requirements |  | 2023-03-10 | bar: 2023-02-24 to 2023-03-10
Validation of results table and download table |  | 2023-03-24 | bar: 2023-03-10 to 2023-03-24
Testing and Validation of Multispectral UI |  | 2023-04-07 | bar: 2023-04-07
Testing functionality and use of checkZipStatus and deleteTempResults for RGB |  | 2023-02-24 | bar: 2023-01-27 to 2023-02-24
Initialization of testing directory manipulation of multispectral data. |  | 3/10/23 | bar: 2023-03-10
Testing checkZipStatus and deleteTempResults for NDVI attribute. |  | 3/24/23 | bar: 2023-03-10 to 2023-03-24
Integration of respective subsystems for RGB attributes. |  | 2023-02-24 | bar: 2023-02-24
Integration of respective subsystems for NDVI attribute. |  | 3/24/23 | bar: 2023-03-10 to 2023-03-24
Integration of respective subsystems for NDRE attribute. |  | 4/7/23 | bar: 2023-03-10 to 2023-04-07
Integration of respective subsystems for MSAVI attribute. |  | 4/7/23 | bar: 2023-04-07
Merging together CSV files for multispectral data. |  | 4/14/23 | bar: 2023-04-14
Merging together SHP files for multispectral data. |  | 4/14/23 | bar: 2023-04-14
Addition of downloadable multispectral data. |  | 2023-04-14 | bar: 2023-04-14